## Sheet1
Knowledge Plan for 2016
Initiatives | Activities | Implemented | periods
|  |  | Q1 | Q2 | Q3 | Q4
Spreading knowledge management culture among FAHR staff | 1. Implementation of training workshops to spread knowledge culture It has been agreed to organize internal workshops through outsourcing staff of FAHR and competent entities. such agreement on workshops aimed at improving the process of quick reading and focus as per Reading Year Initiative directed by Sheikh Mohammed Bin Rashid. |  |  | In progress |  | In progress
| 2. Definition of concepts of knowledge management through e-mail (circulars) Activatation of the role of e-mail by circulating more awareness publications about knowledge management. such publications are to be simplified and able to bring attention of staff for information and indtructions |  | In progress | In progress | In progress | In progress
3. Questionnaires Use of questionnaires periodically to count and identify the favorite activities of staff and the positive proposals as to access to the desirable and suitable methods of staff and gain more benefits
Identification, documentation and making the explicit and implied knowledge assets available for use | 1. Explicit Knowledge Identification Form An Identiofication Form has been prepared for internally explicit knowledge at the level of FAHR by Mr. Ashraf Amayra. This form has been circulated to the departments by Mrs. Nermin. Coordinators have also been identified. A workshop will be identified on how to use the Identiofication Form and compile knowledge as required. |  | Implementation of workshop | Identification of knowledge + launching it on the Portal
Developing an electronic structure supportive to knowledge management | 1. Digital Library - Activate the process of borrowing books among the staff of the Authority and the use of the digital library to download favorit books or share books that were read with the other staff |  | Activation of digital library | Borrowing book | Borrowing book | Borrowing book
| 2. Reading Club Summary of book: An activity through which an employee will talk about a book he has read in order to spread the benefits thereof to everyone |  | Circular for staff | Circular for staff | Circular for staff | Circular for staff
| 3. Activation of knowledge portal on the internal portal An E-mail will be allocated to receive, study and apply proposals in the area of knowledge management if it was useful and innovative. Further, an e-mail will be circulated in this regard. |  | Circulation of e mail to staff of FAHR to receive proposals for knowledge | Reception of proposals | Reception of proposals | Reception of proposals
Launching and activating initiatives that contribute to the spread of knowledge inside and outside FAHR | 1. Book Fair A visit to the book fair will be organized for FAHR employees. Further, a book fair event will be organzied at FAHR. |  | Date of knowledge visit to the book fair will be determined later on
| 2. Knowledge Day One day will be allocated for various knowledge events to be organized at the beginning of the first quarter and the end of the second quarter. Subsequently, an agenda will be put in respect of this Day in the meetings of the team along with the approval on specific days for such event. = Launching the digital library = Launching the knowledge competition |  |  | As per the agenda of FAHR events |  | As per the agenda of FAHR events
| 3. Launch of Knowledge Competition A knowledge competition will be organized at the level of FAHR. The criteria for knowledge management and spread of knowledge will be developped: -Knowledge Leader -Knowledge Officer -knowledge management |  | Circulation of e mail to staff of FAHR to receive proposals for knowledge | Competition date will be determined. Criteria will be determined during the next meeting along with sending prior circulars in this regard
Team Leader. Ali Ahli | Approval of Director General Dr. Abdulrahman Al Awar |  | Team Members (Nermin, Ashraf, Fadil, Amal, Faisal, Mohammed)